## Slide 1: IS6602 VIII: Planning Actions
Creating a Proposal for the Client

## Slide 2: From Diagnosis to Plan
The diagnostic stage may take several weeks, months or longer, since many people may have to be interviewed and many different perspectives reconciled before you feel that you have a complete understanding of the situation
Planning the actions that you want to take is the second AR step and requires considerable care
  It should also be explicitly linked back to the results of the diagnosis
As a consultant, you need to put together a detailed plan that lays out in detail exactly what you propose to do
The plan must be prepared to the highest professional standards
  Well organized, written, attractive, persuasive

## Slide 3: Outline Structure of the Plan I
Background information on the consultants involved
  Experience, skills
  Previous consulting experience (including bios and cvs)
Objectives and Scope
  What are the broad objectives of the plan?
  How will achievement of the objectives be measured?
  Are the objectives feasible? What are the risks?
  Who will benefit (or not) from reaching these objectives?

## Slide 4: Outline Structure II
Actions to be taken
  List the actions in sequence with justification and linkage back to the original needs assessment; draw on theory as appropriate
  Indicate who (internally) needs to be involved and how
  Explain what kind of data needs to be collected so as to assess if actions are successful
  Provide a detailed timetable for the actions
    Milestones, targets, parallel and sequential activities
  Allow for some flexibility in all respects since actions never happen quite as planned
Costs – consulting fees and other expenses

## Slide 5: Six Principles for Preparing a Consulting Proposal
In order to get the proposal right and have a higher chance of being awarded the contract, there are some principles to follow
Don’t forget that consultation tendering is a competitive process
  It is most unlikely that you are the only consultant or firm that hopes to get the contract
If the proposal is in response to an RFP, then you are more constrained in what you can say and if you don’t like what they are asking for, then probably you should not offer a proposal at all.
If the proposal follows a needs assessment exercise, then you can provide a lot more detail
The proposal should be uniquely created for the client - don’t re-use old proposals or cause the client to feel second hand!

## Slide 6: Principle I: Communication
Your proposal should be based on frequent communication with the client
The more often and more deeply you communicate, the better you understand their needs, the better the proposal
You may be able to get client feedback on the proposal before you submit
You should have a better idea of the client’s budget
If you have already formed a good relationship with the client, then the chance of success is much higher
But be careful of clients who want to micromanage the whole project

## Slide 7: Principle II: Perfection A
A huge amount of attention to detail is essential
The proposal must be highly customized, not generic
  You want the client to feel special, so you must create a special proposal
Use language and terminology that the client will understand
  Avoid unnecessary jargon; don’t show off; do demonstrate sensitivity
The writing must be perfect – zero mistakes.
  Clients will not trust you if you make mistakes
The proposal will need to go through several drafts and versions, involving professional proofreaders and copyeditors

## Slide 8: Principle II: Perfection B
Ideally, the proposal can be written with reference to conversations held with the client
  In this way, feedback on specific actions planned can be obtained from the client in advance
  With experience you can learn both what to say and how to say it so as to gain the confidence of the client
Perfect proposals take a lot of time to write, with no guarantee of success
If a proposal is rejected, there is no payment, but hopefully there will be feedback on why it was rejected
  Inside contacts may reveal such feedback informally

## Slide 9: Principle III: Doing What They Asked For - A
It is common sense, but you must aim to do everything that they ask!
This means that you have to read the requirements documents very carefully and ensure that you offer what they want.
  If you don’t understand something, you must ask for clarification.
  If you misunderstand, ignore it, and write up a proposal based on the misunderstanding then you cannot apologise later – there will be no later.
If you think that what they asked for does not make sense, then you can negotiate or ask them to explain
If there was a needs assessment, did they agree with the outcomes?

## Slide 10: Principle III – Doing What They Asked For - B
But what about doing more than they asked for?
  If you think that a RFP is incomplete, then you can try to explain why some further actions are needed.
  This will cost more
    They may be unhappy
    Or they may appreciate that you are thoughtful and careful
  This is why communication is so important
  Unfortunately, RFPs don’t allow much time for communication.
  Clients may even prohibit communication so as to avoid accusations of collusion or favouritism

## Slide 11: Principle IV: Objectives and Targets
Once you have a clear set of client needs (objectives), these need to be translated into initiatives, measures and targets
  Remember the BSC? Objectives; Initiatives; Measures; Targets
  What do you need to do (initiatives) to achieve the objectives at a certain level (measures) of performance (targets)?
  If they cannot be measured, then who knows if they have been achieved?
  Performance data needs to be easy and cheap to collect, preferably quantitatively
  If process changes are expected as an objective, then we need to know exactly what the new processes will look like, so that we can measure them
  Here some creativity is called for since even the client may not know what the outcomes of the actions will be

## Slide 12: Principle V: Be Specific
You need to recommend one or more specific interventions in your proposal so as to give the client a sense of direction
  If you can’t then the client has no idea what is going to happen
  Interventions may need to be modified later
Your proposal should also clearly indicate who will do what
  What are the responsibilities of the client employees?
  What will the consulting team do?
  Some level of collaboration is very likely, so this needs to be set out now
If new resources are required, identify and cost them now
Are the needed skills available?
  Do employees need to learn new skills?

## Slide 13: For Example
Sino Force was a HK-based manufacturer of home entertainment projects (1970s-2000s); now bankrupt and disappeared
It had very out of date processes and systems
They employed consultants who recommended an Oracle ERP
This required a lot of staff training
  The staff were old and had no interest to learn new technologies
It also required cooperation between managers
  But they had no history of cooperation, only fighting!
The project failed

## Slide 14: Principle VI: Outcome Evaluation - A
You need to plan in advance for how the outcomes of the intervention will be evaluated
  What kind of data will you need?
    Perhaps you need to measure employee productivity or satisfaction?
  Triangulative evaluation is useful
    Collect data from multiple perspectives, e.g. employee, manager, customer, system
Evaluation is important because the client wants to be sure that the consulting intervention was effective
A good ROI helps the client to have the confidence that they should try another project – perhaps with you

## Slide 15: Principle VI: Outcome Evaluation - B
A good evaluation is also useful for the consultant
  How well did you do?
  How could you improve?
  What lessons did you learn here that can be applied in future projects?
There are two types of evaluation: Formative and Summative
  Formative: Reflections on the interventions during the process
  Summative: Reflections at the end of the project
Evaluations may involve data from surveys, focus groups, consultant observations, interviews

## Slide 16: Summary
Consulting requires careful, strategic planning
There are several tools that can help this process, but in the end the work has to be done by the consultants
Attention to detail is critical at all stages
Failing to Plan = Planning to Fail
So consultants must provide a high quality proposal with compelling evidence to support it
You must convince the client that the proposed intervention will work and will address the specific client needs

## Slide 17: Costs (Time, Resources, Money) I
Deadlines can be a good motivator, and give the client a sense of what is happening, but they can also push consultants to cut corners
As a general rule, you will always need more time than you think.
Once you have a first estimate of time, double it (at least)!
You will charge the client primarily on time, so if you under budget the time, the cost drops – but then you may not have enough to pay your own costs
You need time for many activities
  Preparation, learning, delivery, follow-up, reports, as well as the solving of unexpected problems

## Slide 18: Costs II
What is your hourly rate?
  And the hourly rate of each person on the consulting team?
Or maybe you charge in 5-minute increments?
Your costs need to be transparent and precise: the client will not want to pay for vague assurances or write you a blank cheque
Are there additional costs?
  Tax? Insurance? Allowances?
  If you need to travel to the client site, then who pays for air tickets, hotels, local transport, etc? Are you flying business class? 5-star hotel?

## Slide 19: Costs III
Costs may also depend on things like
  Did you work for this client before? Do you want to do a small project cheaply or for free so as to create good will and secure a bigger project later?
  How special are the skills that you and your team are offering?
  If the consultants are very experienced, then they can charge a premium
  If they have MSc, PhD, etc. qualifications, then this may also raise the price
  If you are the author of a book on how to do IT consulting, this also raises your profile and cost

## Slide 20: Looks
As a consultant, you need to dress professionally and in line with what the client expects
IT consultants may be more casual if the client is casual as well
  No ties in Silicon Valley!
But smartness and good taste is usually appreciated
  You might need to invest in a nice suit of clothes, etc. if you are consulting for banks, lawyers, and in addition hide piercings, tattoos, etc.
  Other clients may be more open … how about a farming community that is very informal – you will look out of place (and feel hot/sticky) in a suit!
Above all, you should be confident, authoritative, honest and credible
  People who look like experts get more respect, and more work
  Proposals that are meticulously crafted may be rewarded

## Slide 21: Presentations
Your consulting proposal will normally take two forms
A written document
  Many pages of detail that explain your proposal in full
  You may include some of your own market research
A formal presentation
  Where you stand up, as a team, to present your ideas to the client team
  And answer any questions that they may like to ask
  Questions may relate to project details, technicalities, HR issues
  The client team may include managers, users, technical support, CIO

## Slide 22: Presentations
I attended such a presentation recently
The consultants needed to present their ideas about the development of a new website
They first compared the current website with the competition
They then outlined some parameters for development
They talked about the processes that they use, the skills of their team members, the time required, the budget
We asked questions about their ethical values, about their previous clients, about technical details, about their staff turnover
Engaging consultants is like outsourcing
  We want a multi-year relationship

## Slide 23: Summary
Creating a Professional Plan is essential if you are to have any chance of success
This calls for a lot of attention to detail
  The client will quickly find out if you care
  If you don’t care, you don’t deserve to get the client account
Delivering the plan in a professional way is also important, especially if you are meeting senior executives who will make the decision
Don’t be overly confident or arrogant
  Be a little humble, but still confident
  Answer questions very carefully